**Share and develop new models of social care practice that fit the times**

 **SESLIP project plan/brief**

|  |
| --- |
| **PRIORITY/ OBJECTIVE**Share and develop new models of social care practice that fit the times. Authorities are questioning their models of social care practice. Some are seeking to integrate early help and social care and would value some collective thinking about how these services are delivered in this new context. Some large LAs have been spending significant amounts on consultancies to deliver major systems changes. We will investigate the options for shared learning and other collaborative approaches to support new models of practice |
| **OUTPUTS**Dissemination during 2019 of work already undertaken within the region including the Family Safeguarding Model, East Sussex Connected Care model; the Hampshire PiP resilience programme; and Brighton and Hove’s relationship-based approach. Other models will also be included.  To organise a conference to be held in spring 2020, with associated publication of the different models of practice. |
| **SPONSOR**Nikki Edwards – Bracknell Forest |
| **DELIVERABLES*** Overview of models that are currently in use
* Overview of the evidence of success and impact of models of practice
* Understanding of what works and why, within the context of different types of local Authorities
* Understanding of the challenges associated with the models
 |
| **REFERENCE GROUP*** Sonia Johnson
* Ann-Marie Ali
* PSW group – identify champions
 |
| **ESTIMATED TIME & RESOURCES**18 days consultancy Venue and conference costs |
| **BUDGET**2019-20 - £10 000 ( forecast to spend £5600)2020-2021 - £3000 plus budget needed for conference |
| **WORK BREAKDOWN STRUCTURE** |
| **WHAT** | **WHEN** |
| Scope and Agree work plan – set up SESLIP page  | **September 2019** |
| Update PSW contact list and identify champions for reference group | **October 2019** |
| Call for evidence  | **October- November** |
| Review evidence  | **December 2019 – January 2020** |
| Meet PSW to share findings  | **Early February 2020** |
| Plan Spring Conference, Inc. update AD | **February 2020** |
| Hold Spring Conference  | **May 2020** |
| Publish difference models  | **June 2020** |